## Copy of Cover Page
TEAM NAME
Prepared By:
LIST TEAM MEMBER FULL NAMES
Besher AlSabbagh 40313611
Jean-Claude Chiniara 40247594
Carl Abou Nasr 40279011
Nicholas Chamoun 40264135
Valeria Cozonac 40283250
Jerrish Pathmanathan 40317944

## Sheet1
Issue # | User Story Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members | Dependencies
US.6 | As a User I would like to be able to have a profile page |  | 5 | 2026-02-12 | High | High Risk | Carl
Task.6.1 |  | Create API endpoint to retrieve user data (backend) |  |  | High | Medium Risk | Carl | Task.6.4
Task.6.2 |  | display user data (frontend) |  |  | High | High Risk | Carl | Task.6.1, Task.6.3
Task.6.3 |  | Create API endpoint to retrieve user data (backend) |  |  | High | Medium Risk | Carl | Task.6.4
Task.6.4 |  | query user data from database (backend) |  |  | High | Medium Risk | Carl
US.7 | As a user, I would like to delete my account so i can permanently remove my data |  | 3 | 2026-02-13 | High | Medium Risk | Nicholas | US.6
Task.7.1 |  | add "delete account" button on user profile page |  |  | High | High Risk | Nicholas | Task.6.2
Task.7.2 |  | add double validation that user wants to delete the account (frontend) |  |  | High | Medium Risk | Nicholas | Task.7.1
Task.7.3 |  | redirect to login/create account page (frontend) |  |  | High | Low Risk | Nicholas | Task.7.2, Task.7.4
Task.7.4 |  | erase user from database (backend) |  |  | High | High Risk | Nicholas
US.8 | As a user, I would like to have a page where i can see all my recipes |  | 3 | 2026-02-14 | High | Low Risk | Jean-Claude | US.9
Task.8.1 |  | Create button on side menu which redirects user to recipe page |  |  | High | Low Risk | Jean-Claude
Task.8.2 |  | fetch recipes on page load |  |  | High | Medium Risk | Jean-Claude | Task.8.1
Task.8.3 |  | display recipes from database in box style |  |  | High | Low Risk | Jean-Claude | Task.8.2
Task.8.4 |  | add clickable feature on recipe boxes |  |  | High | Low Risk | Jean-Claude | Task.8.3
Task.8.5 |  | handle empty state (no recipes created) |  |  | High | Medium Risk | Jean-Claude | Task.8.2
Task.8.6 |  | display recipe preview on click |  |  | High | Medium Risk | Jean-Claude | Task.8.4
US.9 | As a user, I would like to create a recipe with criteria (time, difficulty, cost, dietary tag, etc) |  | 3 | 2026-02-15 | Medium | Low Risk | Carl
Task.9.1 |  | create a recipe creation form (Front end) |  |  | High | Low Risk | Carl | Task.9.4
Task.9.2 |  | validate form input (front end) |  |  | Medium | Medium Risk | Carl | Task.9.1
Task.9.3 |  | create table on db for recipe (backend) |  |  | High | High Risk | Carl
Task.9.4 |  | create API to add recipe to database (backend) |  |  | Medium | High Risk | Carl | Task.9.5
Task.9.5 |  | save recipe to database (backend) |  |  | High | Medium Risk | Carl | Task.9.3
US.10 | As a user, I would like to edit an existing recipe |  | 3 | 2026-02-16 | Medium | Low Risk | Besher | US.8, US.9
Task.10.1 |  | Add Edit action/button (frontend) |  |  | High | Low Risk | Besher | Task.8.3
Task.10.2 |  | Load recipe into editable form (frontend) |  |  | Medium | Low Risk | Besher | Task.10.1, Task.12.8
Task.10.3 |  | Submit updated recipe (frontend) |  |  | High | Medium Risk | Besher | Task.10.2, Task.10.4
Task.10.4 |  | create API endpoint to update recipe (backend) |  |  | High | Medium Risk | Besher | Task.10.5
Task.10.5 |  | update recipe in database (backend) |  |  | High | Medium Risk | Besher | Task.9.3
US.11 | As a user, I would like to delete a recipe |  | 3 | 2026-02-17 | Low | High Risk | Jean-Claude | US.8, US.9
Task.11.1 |  | Add delete action/button (frontend) |  |  | High | Low Risk | Jean-Claude | Task.8.3
Task.11.2 |  | Add double validation action (front end) |  |  | Medium | Low Risk | Jean-Claude | Task.11.1, Task.11.3
Task.11.3 |  | create API endpoint to delete recipe (backend) |  |  | Medium | Medium Risk | Jean-Claude | Task.11.4
Task.11.4 |  | Update action - update database (backend) |  |  | Medium | High Risk | Jean-Claude | Task.9.3
US.12 | As a user, I would like to search up a recipe from my account by name |  | 2 | 2026-02-18 | Medium | Medium Risk | Valeria | US.8, US.9
Task.12.1 |  | Search bar + results list (front end) |  |  | Medium | Low Risk | Valeria | Task.12.6
Task.12.2 |  | display clickable result list (frontend) |  |  | Low | Low Risk | Valeria | Task.12.1
Task.12.3 |  | create recipe details page |  |  | Low | Low Risk | Valeria | Task.12.2
Task.12.4 |  | handle click -> navigate to selected recipe |  |  | Low | Low Risk | Valeria | Task.12.2, Task.12.3
Task.12.5 |  | display full recipe information |  |  | Low | Low Risk | Valeria | Task.12.4, Task.12.9
Task.12.6 |  | Create search API endpoint (backend) |  |  | Medium | High Risk | Valeria | Task.12.7
Task.12.7 |  | implement database search query/indexing (backend) |  |  | Medium | High Risk | Valeria | Task.9.3
Task.12.8 |  | Create API endpoint to fetch recipe by ID |  |  | Medium | High Risk | Valeria | Task.9.3
Task.12.9 |  | fetch selected recipe data (backend) |  |  | Medium | High Risk | Valeria | Task.12.8
US.13 | As a user, I would like to search up/filter a recipe from my account by time |  | 2 | February 19th | Medium | Medium Risk | Besher | US.12
Task.13.1 |  | Search bar + results list (front end) |  |  | Medium | Low Risk | Besher | Task.13.6
Task.13.2 |  | display clickable result list (frontend) |  |  | Medium | Medium Risk | Besher | Task.13.1
Task.13.3 |  | create recipe details page |  |  | Medium | Low Risk | Besher | Task.13.2
Task.13.4 |  | handle click -> navigate to selected recipe |  |  | Medium | Medium Risk | Besher | Task.13.2, Task.13.3
Task.13.5 |  | display full recipe information |  |  | Medium | Medium Risk | Besher | Task.13.4, Task.13.9
Task.13.6 |  | Create search API endpoint (backend) |  |  | Medium | Medium Risk | Besher | Task.13.7
Task.13.7 |  | implement database search query/indexing (backend) |  |  | Medium | Medium Risk | Besher | Task.9.3
Task.13.8 |  | Create API endpoint to fetch recipe by ID |  |  | Medium | Medium Risk | Besher | Task.9.3
Task.13.9 |  | fetch selected recipe data (backend) |  |  | Medium | Medium Risk | Besher | Task.13.8
US.14 | As a user, I would like to search up/filter a recipe from my account by difficulty |  | 2 | 2026-02-20 | Medium | Medium Risk | Jerrish | US.12
Task.14.1 |  | Search bar + results list (front end) |  |  | Medium | Low Risk | Jerrish | Task.14.6
Task.14.2 |  | display clickable result list (frontend) |  |  | Medium | Medium Risk | Jerrish | Task.14.1
Task.14.3 |  | create recipe details page |  |  | Medium | Low Risk | Jerrish | Task.14.2
Task.14.4 |  | handle click -> navigate to selected recipe |  |  | Medium | Medium Risk | Jerrish | Task.14.2, Task.14.3
Task.14.5 |  | display full recipe information |  |  | Medium | Medium Risk | Jerrish | Task.14.4, Task.14.9
Task.14.6 |  | Create search API endpoint (backend) |  |  | Medium | Medium Risk | Jerrish | Task.14.7
Task.14.7 |  | implement database search query/indexing (backend) |  |  | Medium | Medium Risk | Jerrish | Task.9.3
Task.14.8 |  | Create API endpoint to fetch recipe by ID |  |  | Medium | Medium Risk | Jerrish | Task.9.3
Task.14.9 |  | fetch selected recipe data (backend) |  |  | Medium | Medium Risk | Jerrish | Task.14.8
US.15 | As a user, I would like to search up/filter a recipe from my account by cost |  | 2 | 2026-02-21 | Low | Medium Risk | Valeria | US.12
Task.15.1 |  | Search bar + results list (front end) |  |  | Low | Medium Risk | Valeria | Task.15.6
Task.15.2 |  | display clickable result list (frontend) |  |  | Low | Low Risk | Valeria | Task.15.1
Task.15.3 |  | create recipe details page |  |  | Low | Low Risk | Valeria | Task.15.2
Task.15.4 |  | handle click -> navigate to selected recipe |  |  | Low | Low Risk | Valeria | Task.15.2, Task.15.3
Task.15.5 |  | display full recipe information |  |  | Low | Low Risk | Valeria | Task.15.4, Task.15.9
Task.15.6 |  | Create search API endpoint (backend) |  |  | Medium | High Risk | Valeria | Task.15.7
Task.15.7 |  | implement database search query/indexing (backend) |  |  | Medium | High Risk | Valeria | Task.9.3
Task.15.8 |  | Create API endpoint to fetch recipe by ID |  |  | Medium | High Risk | Valeria | Task.9.3
Task.15.9 |  | fetch selected recipe data (backend) |  |  | Medium | High Risk | Valeria | Task.15.8
US.16 | As a user, I would like to search up/filter a recipe from my account by dietary tag |  | 2 | 2026-02-22 | Low | Medium Risk | Jerrish | US.12
Task.16.1 |  | Search bar + results list (front end) |  |  | Low | Low Risk | Jerrish | Task.16.6
Task.16.2 |  | display clickable result list (frontend) |  |  | Low | Low Risk | Jerrish | Task.16.1
Task.16.3 |  | create recipe details page |  |  | Low | Low Risk | Jerrish | Task.16.2
Task.16.4 |  | handle click -> navigate to selected recipe |  |  | Low | Low Risk | Jerrish | Task.16.2, Task.16.3
Task.16.5 |  | display full recipe information |  |  | Low | Low Risk | Jerrish | Task.16.4, Task.16.9
Task.16.6 |  | Create search API endpoint (backend) |  |  | Medium | High Risk | Jerrish | Task.16.7
Task.16.7 |  | implement database search query/indexing (backend) |  |  | Medium | High Risk | Jerrish | Task.9.3
Task.16.8 |  | Create API endpoint to fetch recipe by ID |  |  | Medium | High Risk | Jerrish | Task.9.3
Task.16.9 |  | fetch selected recipe data (backend) |  |  | Medium | High Risk | Jerrish | Task.16.8