## Copy of Cover Page
TEAM NAME
Prepared By:
LIST TEAM MEMBER FULL NAMES
Besher AlSabbagh 40313611
Jean-Claude Chiniara 40247594
Carl Abou Nasr 40279011
Nicholas Chamoun 40264135
Valeria Cozonac 40283250
Jerrish Pathmanathan 40317944

## Sheet1
Issue # | User Story Title | Task Description | Story Points (1,2,3,5) | Due Date | Priority | Risk | Assignmed Members | Dependencies
US.17 | As a user, I'd like to be able to create a weekly meal plan |  | 5 |  | High | High Risk | Carl | Sprint 1 and Sprint 2
Task.17.1 |  | Weekly Planner Data Model/DB Setup |  |  | High | Medium Risk | Carl | Sprint 1 auth (user id).
Task.17.2 |  | Weekly Planner API: Create plan (Backend) |  |  | High | High Risk | Carl | Task.17.1.
Task.17.3 |  | Weekly Planner UI: Create/select week (Frontend) |  |  | High | Medium Risk | Carl | Task.17.2
Task.17.4 |  | Weekly Planner Create Plan Tests (Backend/integration) |  |  | High | Medium Risk | Carl | Task.17.2.
US.18 | As a user, I would like to be able to view my meals in a weekly grid so that I can see my plan at a glance. |  | 3 |  | High | Medium Risk | Carl | US.17
Task.18.1 |  | Weekly Grid UI (Frontend) |  |  | High | High Risk | Carl | Task.18.2
Task.18.2 |  | Weekly Planner API: Fetch plan by week (Backend) |  |  | High | Medium Risk | Carl | Task.17.1 + Task.17.2.
Task.18.3 |  | Weekly Grid Tests (Frontend/integration) |  |  | High | Low Risk | Carl | Task.18.1 + Task.18.2.
Task.18.4 |  | UI polish + empty-state handling (no meals yet) |  |  | High | High Risk | Carl | Task.18.1.
US.19 | As a user, I would like to assign recipes to a day of the week and a meal type so that my plan is structured. |  | 3 |  | High | Low Risk | Besher | US.17
Task.19.1 |  | Planner UI: Assign recipe to slot (Frontend) |  |  | High | Low Risk | Besher | Task.19.2
Task.19.2 |  | Planner API: Add/assign meal entry (Backend) |  |  | High | Medium Risk | Besher | Task.17.1 + Task.17.2.
Task.19.3 |  | Authorization checks (only owner can modify plan) |  |  | High | Low Risk | Besher | Task.19.2.
Task.19.4 |  | Meal-slot data model adjustments (day + mealType fields) |  |  | High | Low Risk | Besher | Task.17.1.
Task.19.5 |  | Assign flow tests (Backend/integration) |  |  | High | Medium Risk | Besher | Task.19.2 + Task.19.3.
Task.19.6 |  | Recipe selector UX (search/select in modal/dropdown) |  |  | High | Medium Risk | Besher | Task.19.1.
US.20 | As a user, I would like to edit or remove meals from my weekly planner so that I can adjust my plan when things change. |  | 3 |  | Medium | Low Risk | Jerrish | US.19
Task.20.1 |  | Planner UI: Edit/remove actions (Frontend) |  |  | High | Low Risk | Valeria | Task.20.2.
Task.20.2 |  | Planner API: Update/remove meal entry (Backend) |  |  | Medium | Medium Risk | Jerrish | Task.19.2 + Task.19.3.
Task.20.3 |  | Edit/remove tests (Backend/integration) |  |  | High | High Risk | Valeria | Task.20.2.
Task.20.4 |  | Confirmation dialogs + undo/feedback messaging (UI) |  |  | Medium | High Risk | Jerrish | Task.20.1.
Task.20.5 |  | Access control verification for edit/remove |  |  | High | Medium Risk | Jerrish | Task.19.3 + Task.20.2.
US.21 | As a user, I would like to prevent duplicates for the same week so that my plan doesn’t repeat. |  | 3 |  | Medium | Low Risk | Nicholas | US.19
Task.21.1 |  | Duplicate-prevention rules (Backend validation) |  |  | High | Low Risk | Nicholas | Task.19.2.
Task.21.2 |  | UI feedback for duplicate prevention (Frontend) |  |  | Medium | Low Risk | Nicholas | Task.21.1 + Task.19.1.
Task.21.3 |  | DB constraint / uniqueness strategy (if applicable) |  |  | High | Medium Risk | Nicholas | Task.17.1.
Task.21.4 |  | Duplicate-prevention tests |  |  | High | Medium Risk | Nicholas | Task.21.1.
Task.21.5 |  | Docs: explain duplicate rules + edge cases |  |  | High | Medium Risk | Nicholas | Task.21.1.
US.22 | As a user, I would like a unique feature so that MealMajor provides value beyond basic meal planning. |  | 3 |  | Low | High Risk | Valeria | TA approval.
Task.22.1 |  | Unique Feature Proposal (description + scope) |  |  | High | Low Risk | Valeria
Task.22.2 |  | Unique Feature Implementation (Full stack) |  |  | Medium | Low Risk | Valeria | Task.22.1 + TA approval.
Task.22.3 |  | Unique Feature Acceptance Tests (AT issues) |  |  | Medium | Medium Risk | Carl | Task.22.1.
Task.22.4 |  | TA approval + scope confirmation (record decision) |  |  | Medium | High Risk | Valeria | Task.22.1.
US.23 | Process Requirements (tests, ATs, CI, minutes, logs) |  | 2 |  | Medium | Medium Risk | Jean-Claude | US 17, US 18, US 19
Task.23.1 |  | Write 2 Acceptance Tests (AT) for Sprint 2 user stories (link US → Task) |  |  | Medium | Low Risk | Jean-Claude | Sprint 2
Task.23.2 |  | Create/ensure unit tests for Sprint 1–2 features and run them on CI |  |  | Low | Low Risk | Jean-Claude
Task.23.3 |  | Upload meeting minutes |  |  | Low | Low Risk | Jean-Claude
Task.23.4 |  | Individual contribution logs (time per activity) |  |  | Low | Low Risk | Jean-Claude
Task.23.5 |  | CI pipeline verification (tests run on PR + main) |  |  | Low | Low Risk | Jean-Claude | Task.23.2.
Task.23.6 |  | Repo hygiene: update README with Sprint 3 setup/run steps |  |  | Medium | High Risk | Jean-Claude
Task.23.7 |  | Demo preparation for Sprint 3 (script + stable data) |  |  | Medium | High Risk | Jean-Claude
Task.23.8 |  | Backlog grooming + dependency check for Sprint 4 |  |  | Medium | High Risk | Jean-Claude
Task.23.9 |  | QA pass: cross-browser / edge-case testing |  |  | Medium | High Risk | Jean-Claude | UI tasks.
US.24 | As a user see calories for each meal |  | 4 |  | Medium | Medium Risk | Besher
Task.24.1 |  | Add calories column to meals table |  |  | Medium | Medium Risk | Besher
Task.24.2 |  | Ensure all existing meals have a value (default or computed) |  |  | Medium | Medium Risk | Besher
Task.24.3 |  | Update GET /meals endpoint to include calories |  |  | Medium | Medium Risk | Besher
Task.24.4 |  | Ensure calories are: stored when creating meals |  |  | Medium | Medium Risk | Besher
Task.24.5 |  | Validate calorie input (must be positive number) |  |  | Medium | Medium Risk | Besher
Task.24.6 |  | Update meal UI component to display calories |  |  | Medium | Medium Risk | Besher
Task.24.7 |  | Add label: XXX kcal |  |  | Medium | Medium Risk | Besher
Task.24.8 |  | Add color indicator (low/medium/high) |  |  | Medium | Medium Risk | Besher
US.25 | As a user i would like calculations of my BMI |  | 3 |  | Medium | Medium Risk | Nicholas
Task 25.1 |  | Create endpoint POST /bmi |  |  | Medium | Low Risk | Nicholas
Task 25.2 |  | Implement BMI formula |  |  | Medium | Low Risk | Nicholas
Task 25.3 |  | Add validation: height/weight |  |  | Medium | Low Risk | Nicholas
Task 25.4 |  | return BMI Value |  |  | Medium | Low Risk | Nicholas
Task 25.5 |  | Store BMI Value in the Databse |  |  | Medium | Low Risk | Nicholas
Task 25.6 |  | Update the user information database adding a row for the BMI |  |  | Medium | Low Risk | Nicholas
Task 25.7 |  | Create BMI input form:weight input / height input |  |  | Medium | Low Risk | Nicholas
Task 25.8 |  | Add “Calculate” button |  |  | Medium | Low Risk | Nicholas
Task 25.9 |  | Display result dynamically |  |  | Medium | Low Risk | Nicholas
US.26 | As a user i would like to be alerted when weekly calorie goal exceeded |  | 3 |  | Medium | Medium Risk | Carl
Task 26.1 |  | Add weekly_calorie_goal to users table |  |  | Medium | Medium Risk | Carl
Task 26.2 |  | Ensure meals have date field |  |  | Medium | Medium Risk | Carl
Task 26.3 |  | Create function to calculate weekly calories |  |  | Medium | Medium Risk | Carl
Task 26.4 |  | Create logic to compare: total calories vs goal |  |  | Medium | Medium Risk | Carl
Task 26.5 |  | POST /meals → check after adding meal |  |  | Medium | Medium Risk | Carl
Task 26.6 |  | Return alert flag in API response |  |  | Medium | Medium Risk | Carl
Task 26.7 |  | Display alert message when exceeded |  |  | Medium | Medium Risk | Carl
Task 26.8 |  | Add UI for setting calorie goal |  |  | Medium | Medium Risk | Carl
Task 26.9 |  | Show:current total /goal |  |  | Medium | Medium Risk | Carl
[5 empty] | Medium | Medium Risk | Carl
[5 empty] | Medium | Medium Risk | Carl
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weekly Meal Planner Create a weekly meal plan View meals in a weekly grid Assign recipes to: Day of the week Meal type (breakfast/lunch/dinner/snack) Edit or remove meals from the planner Prevent duplicates for the same week Your unique team feature.