## Cover Page
TEAM NAME
Prepared By:
LIST TEAM MEMBER FULL NAMES
Besher AlSabbagh 40313611
Jean-Claude Chiniara 40247594
Carl Abou Nasr 40279011
Nicholas Chamoun 40264135
Valeria Cozonac 40283250
Jerrish Pathmanathan 40317944

## Product backlog
Issue # | User Story Title/Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members
#1 | As a user, I would like to be able to create an account or login into my account to acces my information | - HTML page for login + css for styling - Create database | 4 | 2026-02-04 | High | HIGH - Needs to be done first to be able to do the rest | - Besher - Jerrish - Nicholas
#2 | As a user I would like to be able to enter my diet preferences and allergies on my profile | -Allow the user to select from a list of common allergies seperated by caterogies. -Also allow user to add an allergy if it is not in the predefined list | 4 | 2026-02-05 | High | HIGH - needs to be implemented to be able to create the account accurately | -Carl -Jean Claude -Valeria
#3 | As a user I shoud be able to delete my account if I wish to stop using the website | -Delete account page with a database that access's all user information | 2 | 2026-02-06 | High | low - doesn't inhibit further development | - Besher
#4 | Story 3: |  |  |  | High
#5 | Story 3: |  |  |  | High
#6 | Story 4: |  |  |  | High
|  | Total | 10